Communication Plan:  Kansas Statewide Infant Mortality Campaign:  Fall 2011

Purpose:  Increase awareness about the seriousness of infant mortality as a public health issue in Kansas

Primary Audience:  Kansas Blue Ribbon Panel on Infant Mortality Representatives and Coalition and Community Partners from private and public sectors

Secondary Audiences:  Community members in target populations at risk for infant mortality (women under 20 years-of-age, single parents, less than high school level education; African American mothers and fathers; childcare providers)

Strategies:

- Intensify messaging about infant mortality in Kansas through delivery of materials and resources for local campaigns in Kansas City, Topeka, Wichita and regional non-urban focus areas – Geary, Saline, Butler, Elk, Greenwood, and Chautauqua Counties.

- Based on materials and resources provided from the statewide marketing and media toolkits, support development of local campaigns through consultation with statewide coordinators (Aiko Allen and Christy Schunn)

Duration:  Three Month Initial Campaign (September: Infant Mortality; October: SIDS; November: Prematurity) followed by “booster” campaign in spring

Potential Measurement:

- Number of media impressions (audience reach estimates per TV, radio, magazine, newspaper, etc.)

- Number of articles and interviews in media (includes TV, radio, newspaper, magazines, newsletters, bulletins, e-newsletters, etc.)

- Number of presentations

- Number of materials distributed

- Number of Press Releases

- Number of communities (e.g, local health departments) that develop and implement campaigns

- Number of website hits

- Number of websites that carry “banner” titles, links, articles, etc.

- Number of participants at presentations/trainings

- Number of proclamations

- Frequency of media messages (number and duration)

Materials:

- Media  and marketing tool kits (PSA and press release templates; proclamation template; fact sheets for multiple audiences)

- Powerpoint presentations

- Postcards, posters

- Website links to  national, state, local resources

- “How-to” guide for conducting a campaign

| Deliverable/Description | Type | Target Audience(s) | Delivery Method | Delivery Frequency | Who Responsible? |
| --- | --- | --- | --- | --- | --- |
| August - Update statewide campaign information - Review Kansas Blue Ribbon Panel on Infant Mortality website campaign resources and revise as needed - Select primary message for the infant mortality campaign that can be used among partners and in media kit and on websites | Marketing | KS Blue Ribbon Panel reps and coalition partners; community agencies, community members | Media kits and educational materials available through Blue Ribbon Panel website; KDHE (to be determined but including KDHE home page, Bureau of Family Health at minimum); Blue Ribbon Panel members; community agencies | Released by mid-August | Aiko Allen, Christy Schunn, Connie Satzler Community agency staff/directors BrushArt consultation |
| September - Assessment of inter-related campaigns – metro campaigns in 3 cities and statewide - Timeline developed and activities - Gaps and opportunities identified - Resources leveraged | Marketing | Metro campaign planners | Meet with campaign planners to be informed of components and how state campaign coincides and strengthens local campaigns Evaluate leveraging of resources – particularly earned media and what can be done to amplify messages | Meet a minimum of one time prior to launch dates to coordinate campaign components | Aiko, Christy, campaign planners-Healthy Start coordinators Wichita, KC |
| - Governor’s Proclamation (and/or community proclamation) submitted and signed - Governor’s signing ceremony | Marketing | KS communities | Proclamation drafted and scheduled for signing Signing Ceremony, TBA | Signed for use during the month as appropriate | Aiko, Miranda Myrick |

| Deliverable/Description | Type | Target Audience(s) | Delivery Method | Delivery Frequency | Who Responsible? |
| --- | --- | --- | --- | --- | --- |
| September - Infant Mortality Awareness Month “button” on KDHE homepage and link to SIDS Network KS, Blue Ribbon Panel and Bureau of Family Health - Campaign kits and resources related to infant mortality on KDHE Bureau of Family Health website link - Email to Blue Ribbon Panel members to announce campaign - Blue Ribbon Panel members and community agencies post toolkit to their websites | Info | KS communities, public health staff | KDHE website At mimimum materials posted (toolkits with sample proclamation, letters to editor, fact sheet, swiss cheese press release, powerpoint presentation on infant mortality, links to other resources and programs) Panel and community agency websites carry links to toolkits | Evaluated weekly 3months | Jeff Rozwick, KDHE webmaster, Aiko Aiko, Christy, Connie, Dave Agency webmasters |
| September - Local health departments carry local campaign materials on their websites - Health Department programs such as “Safe Kids” carry campaign materials on their websites, Tobacco Use Prevention, Child Care Licensing, etc. | Info | KS communities | Health department websites KDHE program websites | 3 months 3 months | Aiko KDHE program managers |
| September - Track campaign activities – develop and use tracking log for activities - Deliver tracking logs to Aiko Allen at end of each campaign month so efforts can be assessed statewide - Create a summary of each month’s campaign statewide- successes and challenges | Info | Panel Reps and community partners | Include an activity tracking log with the media kit so that activity reach and exposure can be evaluated (message saturation, frequency, etc) For each Blue Ribbon Panel member and community agency that undertakes a campaign and community agency staff, assign a contact person to track activities and events and to work with Aiko as these logs are collected | Evaluated bi-weekly | Panel reps Aiko |

Replicate campaign in October and November.

- Develop a summary report for campaign activities across the three month period for distribution among Panel agencies and coalitions and community agencies.

- Share lessons learned.

- Prepare for Spring “booster” session 2012