PRAMS - pregnancy risk assessment monitoring system - Startup Schedule

First Year

FALL

Hire two staff - Coordinator, Data Manager

Obtain CDC training and TA for staff

Write protocols and finalize data sharing agreements

Prepare and print introductory letters, survey instrument and accompanying letters

Decide whether to offer incentives for participation in survey to improve response rate

SPRING

Mail introductory letters in Spring - approx 2,500

Second Year

FALL

Follow-up on non-respondents - mail survey up to three times to each woman

If no response to mailings, phone - up to 15 times each

Conduct data cleanup and data entry into CDC on-line system

SPRING

Mail introductory letters in Spring - approx 2,500

Third Year

FALL

Follow-up on non-respondents - mail survey up to three times to each woman

If no response to mailings, phone - up to 15 times each

Conduct data cleanup and data entry into CDC on-line system

CDC weights data from previous year and sends back to Kansas

Kansas analyzes data and writes report

Publication and recommendations

Review protocols and materials

Revision as necessary

SPRING

Mail introductory letters - approx 2,500

Fourth Year

Repeat 3rd year - ongoing

4-11