Version 2-18-11

Kansas Blue Ribbon Panel on Infant Mortality—Putting Our Logic Models to Use

| STRATEGY: Promoting Awareness of Problem of Infant Mortality and How to Assure Healthy Babies for All |  |  |  |  |
| --- | --- | --- | --- | --- |
| SPECIFIC ACTIVITIES | WHO | Will Do WHAT | By WHEN | STATUS |
| Infant mortality awareness campaign - develop overall communication plan - collaborate with partners | Partner organizations (e.g. Sept - Healthy Start, Oct - SIDS, Nov -MOD) | Local and state-level efforts; followed overall BRP framework; used national resources | Sept – Nov 2010 | Completed |
| Infant mortality awareness Part II – Tonya Lewis Lee Tour | 3 host coordinators Healthy Start in Wichita AA Affairs in Topeka MCHC in KC | Will cover today - press conversations, other media events - community activities - community, health professionals & providers, and legislature – 3 targets for awareness | April 2011; gear-up in March, after-effects in May | Final planning underway; collaborative effort |
| Target these three groups in awareness activities - Community - Health professional organizations, health providers - Legislature & policy makers |  |  |  |  |
| Development of web tools to have current and updated information. |  |  |  |  |
| Develop, disseminate, and train health professions, parents, and care providers how to prevent SIDS and promote safe sleep |  |  |  |  |
| Collaborate with other KDHE divisions and other partners on related issues (e.g., TUPP, Tobacco Free Kansas on tobacco prevention) | Aiko, Center for Health Disparities |  |  |  |
| STRATEGY: Advocacy for Improving Conditions to Assure Healthy Babies |  |  |  |  |
| SPECIFIC ACTIVITIES | WHO | Will Do WHAT | By WHEN | STATUS |
| Advocate to assure restructuring of Medicaid plan is consistent with Panel’s goals |  |  |  |  |
| STRATEGY: Advocacy for Improving Conditions to Assure Healthy Babies, continued |  |  |  |  |
| SPECIFIC ACTIVITIES | WHO | Will Do WHAT | By WHEN | STATUS |
| Meet with new Administration members to - Advocate for Panel’s priorities with Dr. Moser - Advocate for Panel’s priorities with Insurance Commissioner - Advocate for Panel’s priorities with Governor, working through Lt. Gov. Colyer |  | Dr. Moser: Diane Daldrup & Dr. Cooley will meet with him. Linda & Aiko continue to provide information to the Secretary internally. |  |  |
| Immediate risk: Advocate with legislature to ensure we meet maintenance of effort requirement. Immediate priority for CHIP shortfall of $3 million that has yet to be filled in Senate Ways and means for 2011 (current fiscal year). |  |  |  |  |
| Identify champions: - Legislative - Parents - Business |  |  |  |  |
| STRATEGY: Guide and Legitimize State and Local Work |  |  |  |  |
| SPECIFIC ACTIVITIES | WHO | Will Do WHAT | By WHEN | STATUS |
| Aiko (CHD), Diane (MOD), others are using to guide and legitimize their work. |  |  |  |  |
| STRATEGY: Pursue Grant Opportunities to Support this Work |  |  |  |  |
| SPECIFIC ACTIVITIES | WHO | Will Do WHAT | By WHEN | STATUS |
| NICHD might be interested in comprehensive effort involving multiple partners and types of initiatives |  |  |  |  |
| REACH Foundation as possible funder for FIMR expansion in Wyandotte Co. |  |  |  |  |