Action Plan for Goal #2:  Promote collaborative partnerships in support of genetic services in Kansas.

Three key steps to implementing this goal:

- Identify stakeholders, both professionals and organizations.

- Evaluate infrastructure available for connectivity among stakeholders, including telemedicine, listservs, etc.

- Improve dissemination of information and accessibility to genetics resources for stakeholders.  Strengthen network of genetics services and resources for Kansas.

| Objective/Step | Priority (High, Med, Low) | Action Recommended | First Step (if different from Action Recommended) | Current Resources Available | Responsible Person or Org. | Implementation Timeline (By When?) |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Promote collaborative partnerships between hospitals, educational institutions and health care professionals to support genetic services and education | High |  |  |  | KDHE & Genetics Stakeholders |  |
| 1a. Identify professionals and organizations in Kansas that are interested in participating and supporting genetic services | High | Survey both clinical and educational institutions |  | Similar survey done by KDHE in 2005. Consider updating it |  | 1 year |
| 1b. Assess interest and need for connecting clinics/ organizations/ institutions providing genetic services and education in Kansas | High | Survey both clinical and educational institutions |  | None |  |  |
| 1c. Identify cost effective modalities for linking stakeholders | High | Evaluate effective communication methods such as listserv or televideo calls |  | Currently no listserv exists that is specific to genetics in Kansas |  |  |
| 1d. Conduct annual genetics update symposium in Kansas to update local health care professionals and educational institutions | Low | Small symposium or conference annually or every two years to bring together genetics experts in Kansas. Consider partnering with AAP or AAFP |  |  |  |  |
| 2. Increase utilization of telegenetics for clinical and educational purposes | High |  |  |  |  |  |
| 2a. Assess telemedicine capability of hospitals and organizations participating in genetic services in Kansas |  |  |  | Heartland conducted a telegenetics survey in 2007 but it was incomplete/ needs updating |  |  |
| 2b. Survey organizations and professionals about their perception, acceptance and need for telemedicine |  |  |  |  |  |  |
| 2c. Encourage setting up telemedicine in rural hospitals to increase access to genetics services |  |  |  | Heartland grant funding |  |  |
| 3. Identify and pursue use of telemedicine as a tool for improving accessibility and dissemination of information and resources. |  |  |  |  |  |  |
| 3a. Improve accessibility and dissemination of information about resources and services to families of children with or at risk for birth defects and heritable disorders. |  | Overlaps with Goal 3 – create website | Compile information Develop Website Post online |  |  |  |
| 3b. Provide resources for uniform information for all families of children with a genetic diagnosis. |  | Overlaps with Goal 3 – create website | Compile information Develop Website Post online |  |  |  |
| 3c. Disseminate resources and services information to all pediatricians, family physicians, pediatric and family nurse practitioners, nurse midwives, and registered nurses and interpretive services. |  | Overlaps with Goal 3 – create website | Compile information Develop Website Post online |  |  |  |
| 3d. Assess unmet informational and resource needs and utilization of existing brochures by hospital social workers and neonatal intensive care units. |  |  |  |  |  |  |
| 3e. Include translators and interpreters in the development and dissemination of information about resources and services. Provide information and/or training so they are familiar with genetics terminology. |  |  |  |  |  |  |
| 4. Promote/enhance/improve/ standardize quality and availability of clinical reproductive genetic services statewide and disseminate consensus guidelines for reproductive genetic health care. |  |  |  |  |  |  |
| 4a. Promote use of the guidelines by primary and specialty health care providers serving women of reproductive age, in order to increase utilization of birth defect prevention strategies and appropriate reproductive genetic screening techniques statewide. |  |  |  |  |  |  |
| 4b. Identify best practice guidelines for medical management of common genetic conditions and birth defects diagnosed prenatally. |  |  |  |  |  |  |
| 4c. Assist primary care providers in assuring appropriate follow-up of abnormal prenatal tests. |  |  |  |  |  |  |
| 4d. Provide genetics training for obstetric/gynecological professionals, including physicians, nurses, and/or administrative staff. |  |  |  |  |  |  |
| 4.e. Disseminate standardized resource materials. |  |  |  |  |  |  |