## CYSHCN Logic Models
Children & Youth with Special Health Care Needs Logic Model
VISION - Healthy Children in Healthy Families
MISSION - Provide leadership to enhance the health of Kansas women and children in partnership with families and communities.
GOAL STATEMENT: To enhance the health of all children and youth with special health care needs across the lifespan.
PRIORITY OBJECTIVE #1: All CYSHCN receive coordinated, comprehensive care within a medical home.
Planned Activities/Action Steps |  | Outputs | Short-Term Outcomes | Intermediate Outcomes | Long-Term Outcomes
1.1 | Strategy: | Inform, educate, and involve families and providers about medical home components and initiatives to promote effective and successful systems change.
Essential MCH Service (select from list): |  | 3. Inform/educate the public/families about MCH issues
1.1.1 | Identify and assess available information, including best practices, programs in other states, national medical home initiatives, etc. | Medical home definition and supporting information disseminated through CYSHCN and partner publications | Providers and families are aware of statutory definition of medical home and have changed attitude toward medical home, giving it increased value | Statutory definition of medical home adopted and utilized by providers and families. | All CYSHCN receive coordinated, comprehensive care within a medical home.
1.1.2 | CYSHCN program promotes the adoption of a medical home through education and self-advocacy training. | Provide trainings to educate families and providers regarding the medical home concepts and how to build a medical home. | Families and providers are empowered with changed attitudes and increased knowledge about the medical home concept. Stakeholder and partners are empowered and invested, promoting actions, including policy and practice changes related to increased care within a medical home. | Behaviors, practices, and policies facilitate/reflect all CYSHCN receiving care within a medical home.
1.1.3 |  | Provide workshops to practice self-advocacy and share information with peers on the positive impact of medical home concept for both families and providers. |  | Increased number of CYSHCN receive care within a medical home.
1.2 | Strategy: | Mobilize community partnerships (between policy makers, health care providers, families, and the public) by coordinating services for eligible CYSHCN and linking children and families to providers and community services/resources.
Essential MCH Service (select from list): |  | 4. Mobilize community partnerships to solve MCH issues
1.2.1 | Sponsor and coordinate conferences, meetings, and other networking opportunities | (1) Multi-state collaborative conference on medical home (2) Serve on stakeholder groups (3) Coordination/facilitation of Advisory Councils (4) Support of multidisciplinary, special needs clinics (5) Sponsorship of learning collaboratives MADIN utilized to help improve linkages and collaboration | Stakeholder and partners are empowered and invested, promoting actions, including policy and practice changes related to increased care within a medical home. | Behaviors, practices, and policies facilitate/reflect all CYSHCN receiving care within a medical home. Increased coordination and improved, comprehensive care provided within medical home. | All CYSHCN receive coordinated, comprehensive care within a medical home.
PRIORITY OBJECTIVE #2: Improve the capacity of YSHCN to achieve maximum potential in all aspects of adult life, including appropriate health care, meaningful work, and self-determined independence.
Planned Activities/Action Steps |  | Outputs | Short-Term Outcomes | Intermediate Outcomes | Long-Term Outcomes
2.1 | Strategy: | Enhance community partnerships by identifying community resources, integrating service delivery systems, and streamlining the transition process for children and youth.
Essential MCH Service (select from list): |  | 4. Mobilize community partnerships to solve MCH issues
2.1.1 | Identify available local, regional, state, and national resources. | (1) Develop and disseminate a regional and state-wide resource tool kit and navigational guide. Provide maintenance and updates as necessary. (2) MADIN utilized to help improve linkages and collaboration with regard to transition services. | Families, youth, and service providers are empowered with increased knowledge and changed attitudes about available transition services and how to access these services. Stakeholders play an active role in sharing and disseminating information regarding resources to other organizations, families, and youth. | The service delivery systems in Kansas are integrated, reducing fragmented care and are easily accessible by CYSHCN and their families. | Improved capacity of YSHCN to achieve maximum potential in all aspects of adult life, including appropriate health care, meaningful work, and self-determined independence.
2.1.2 | Participate in and sponsor conferences, meetings, and other networking opportunities related to the transition process. | (1) Coordinate multi-state collaborative conference on health care transition. (2) Serve on stakeholder groups (3) Expand program advisory councils as appropriate to promote further integration and collaboration. (4) Participate and support other transition-related events and activities. |  | Increased number of CYSHCN receive services necessary for transitions.
2.2 | Strategy: | Inform and educate children, youth, and families about available transition services and where/how to access these services.
Essential MCH Service (select from list): |  | 7. Link women & children with services and assure quality systems of care
2.2.1 | Identify available local, regional, state, and national resources. | (1) Develop and disseminate a regional and state-wide resource tool kit and navigational guide. Provide maintenance and updates as necessary. (2) MADIN utilized to help improve linkages and collaboration with regard to transition services. | Youth and families have a positive outlook on reaching their full potential and are aware of transition resources and supports. | Families utilize available resources and supports to enhance their child(ren)'s transition process so they can reach their full potential as adults. Increased number of CYSHCN receive services necessary for transitions. | Improved capacity of YSHCN to achieve maximum potential in all aspects of adult life, including appropriate health care, meaningful work, and self-determined independence.
2.2.2 | Promote successful transition through educational opportunities and self-advocacy training. | (1) Recruit and maintain a Youth Advisory Council and provide opportunities to enhance leadership and self-advocacy skills. (2) Provide learning opportunities for families, youth, and partners on all aspects of transition. (3) Promote self-determination in transition planning through the use of a curriculum or planning instrument. | Youth and families are engaged and active participants on advisory councils and state initiatives.
2.2.3 | Identify, assess, and disseminate information and materials from local, regional, state, and national transition initiatives. | (1) Transition initiatives and supporting information disseminated through CYSHCN and partner publications. (2) Develop or adopt transition materials to disseminate to providers, families, and partners. | Youth and families are empowered with increased knowledge on accessing and utilizing services to enhance the transition process.
PRIORITY OBJECTIVE #3: Financing for CYSHCN services minimizes financial hardship for their families.
Planned Activities/Action Steps |  | Outputs | Short-Term Outcomes | Intermediate Outcomes | Long-Term Outcomes
3.1 | Strategy: | Link families to providers who are contracted with or referred by the CYSHCN program and accept negotiated reimbursement rates.
Essential MCH Service (select from list): |  | 7. Link women & children with services and assure quality systems of care
3.1.1 | Monitor, assess, and evaluate federal and state policies as they relate to health coverage and services. | (1) Information and updates are disseminated on websites, in newsletters, and other publications. (2) Regular updates are provided at internal and community meetings identifying anticipated impact on coverage and services. (3) Workshop(s), training(s), and materials are offered informing partners in how to advocate and change policy. (4) Kansas services and coverage's are benchmarked in relation to other states and peer groups. | Stakeholder and partners are informed, empowered, and invested, promoting actions - including policy and practice changes, when necessary - resulting in maximized services to families and reimbursements to providers. | CYSHCN policies are aligned with federal policies/mandates to maximize services to families and reimbursements to providers. | Financial hardship is minimized for families with CYSHCN.
3.1.2 | Provider outreach and education | (1) See 3.1.1 outputs above, as applicable (2) CYSHCN program collects and provides Kansas-specific information on barriers and challenges to state and national professional and stakeholder organizations. (3) The impact of national and state professional organization recommendations on Kansas is assessed; appropriate information is disseminated to providers. | See 3.1.1 outcomes above, as applicable Increased provider pool that accepts CYSHCN-defined target rate(s) of reimbursement.
3.1.3 | Staff and Consumer education | See 3.1.1 outputs | See 3.1.1 outcomes
3.1.4 | Educate and mobilize Families Together, Family Advisory Council, and other partners and stakeholder groups. | See 3.1.1 outputs | See 3.1.1 outcomes
3.2 | Strategy: | Ensure CYSHCN Clinic/Field staff assist families in applying for and maximizing benefit of funding sources and family supports.
Essential MCH Service (select from list): |  | 9. Evaluate effectiveness, accessibility, quality
3.2.1 | Staff education | (1) Regular updates are provided at internal meetings identifying anticipated impact of health reform on coverage and services. (2) Staff monitors listservs, KS-Train, national resources to stay current. (3) Staff receives training and information on cultural competency/preferences. | (1 & 2) Staff shares relevant information with families and youth. (3) Staff incorporates cultural competency/preferences when assisting families in applying for funding sources. | Families utilize resources and family supports to minimize financial hardships. | Financial hardship is minimized for families with CYSHCN.
3.2.2 | Identify, assess, and monitor resources at the state and local level. | Regular, ongoing communication regarding resources takes place among staff. | Staff and community partners engaged in assisting families in identifying and applying for possible funding sources and family supports.
3.3 | Strategy: | Support expansion of primary and specialty care services to minimize travel time and missed work/school days.
Essential MCH Service (select from list): |  | 5. Leadership in setting priorities, planning and policy development
3.3.1 | Needs assessment of primary and specialty care services, current utilization, and gaps to service delivery | (1) Explore service expansion options, including alternative and innovative solutions (2) Regional specialty clinic implementation plan developed | Specialty care services are accessible and integrated within a regional service delivery area. | Primary and specialty providers coordinate services and information for expedited care and minimal family hardship. | Financial hardship is minimized for families with CYSHCN.

## CYSHCN Workplan
Children & Youth with Special Health Care Needs Work Plan
VISION - Healthy Children in Healthy Families
MISSION - Provide leadership to enhance the health of Kansas women and children in partnership with families and communities.
GOAL STATEMENT: To enhance the health of all children and youth with special health care needs across the lifespan.
PRIORITY OBJECTIVE #1: All CYSHCN receive coordinated, comprehensive care within a medical home.
Indicator(s) for Priority Objective #1
A. | Percentage of CYSHCN who receive care in medical home as defined by AAP
B. | Percentage of CYSHCN who receive care in medical home |  |  | Indicator selected during small group work
C. | Percentage of CYSHCN aged 2-17 with problems requiring counseling who received mental health care
D. | Percentage of CYSHCN who receive BOTH routine preventive medical and dental care visits?
E. | Percentage of CYSHCN who had at least one unmet medical need
F. | Percentage of CYSHCN who have at least one need for specific health services
G. | Percentage of CYSHCN who have at least one need for family supportive services
H. | Percentage of CYSHCN who had difficulty getting a referral
I. | Percentage of CYSHCN who had difficulty getting a referral
J. | Percentage of CYSHCN aged 1-17 who at least one oral health problem in past 6 months
K. | Percentage of CYSHCN aged 6-17 who have medical, behavioral or other health conditions which interfere with their ability to attend school regularly, participate in sports or other activities, or make friends
SPM #8 | Percent of CYSHCN who receive care in a medical home as defined by the American Academy of Pediatrics (AAP) - NSCH
| Activities/Action Steps | Completion Date for Activity | Responsible Party
1.1 | Inform, educate, and involve families and providers about medical home components and initiatives to promote effective and successful systems change. |  | Mary Ann Bechtold
1.1.1 | Identify and assess available information, including best practices, programs in other states, national medical home initiatives, etc.
OUTPUT | Medical home definition and supporting information disseminated through CYSHCN and partner publications | (a) Current and ongoing: Monitor what is being presented by national, state, and local partners. (b) Current and ongoing. Strengthen relationships with partners and listen to their concerns and activity focus to integrate resources (c) Develop/disseminate articles about medical home for internal publications (e.g., CYSHCN magazine, column to newsletter), starting Summer 2010. (d) Develop/disseminate template articles and information for distribution through partner publications by June 2011.
| Activities/Action Steps | Completion Date for Activity | Responsible Party
1.1.2 | CYSHCN program promotes the adoption of a medical home through education and self-advocacy training.
1.1.3
OUTPUT | (1) Provide trainings to educate families and providers regarding the medical home concepts and how to build a medical home. (2) Provide workshops to practice self-advocacy and share information with peers on the positive impact of medical home concept for both families and providers. | (0) Engage families and partners in identifying training and workshop content during Fall 2010 (base development) and ongoing (updates to curriculum). (1)(a) Develop training curriculum by March 2011. (1)(b) Pilot training by June 2011. (1)(c) Finalize training curriculum and begin broad delivery by September 2011. (2)(a) Develop workshop curriculum by March 2012. (2)(b) Partner with stakeholders to implement workshops by September 2012.
1.2 | Mobilize community partnerships (between policy makers, health care providers, families, and the public) by coordinating services for eligible CYSHCN and linking children and families to providers and community services/resources. |  | Mary Ann Bechtold
1.2.1 | Sponsor and coordinate conferences, meetings, and other networking opportunities
OUTPUT | (1) Multi-state collaborative conference on medical home (2) Serve on stakeholder groups (3) Coordination/facilitation of Advisory Councils (4) Support of multidisciplinary, special needs clinics (5) MADIN utilized to help improve linkages and collaboration | (1a) Serve on planning work group, April 2010. (1b) Co-host transition and medical home collaborative, Summer 2011. (1c) Evaluate and assess the benefit of the collaborative, Fall 2011. (1d) Determine, as a work group, if future collaboratives would be beneficial and how frequent they should occur, upon analysis of collaborative (Fall 2011) (2) Current and ongoing (3) Current and ongoing (4) Current and ongoing (5) Current and ongoing
PRIORITY #2: Improve the capacity of YSHCN to achieve maximum potential in all aspects of adult life, including appropriate health care, meaningful work, and self-determined independence.
Indicator(s) for Priority Objective #2
A. | Percentage YSHCN (12-17 years) who receive the services necessary to make appropriate transitions to adult health care, work and independence
B. | Percentage of recipients successfully transition from Part C to Part B
C. | Percentage YSHCN receive all anticipatory guidance for transition to adult health care |  |  | Other indicators selected during small group work
D. | Percentage YSHCN whose doctors usually or always encourage development of age appropriate self management skills
E. | Percentage of CYSHCN program (15 and older) participants who found an adult doctor
F. | Percentage of CYSHCN program (15 and older) participants who found an adult specialist
G. | Percentage of CYSHCN program (15 and older) participants who know when to report changes in their health
H. | Percentage of CYSHCN program (15 and older) participants who know how to get emergency help
I. | Percentage of CYSHCN program (15 and older) participants who can take responsibility for their health needs at home
J. | Percentage of CYSHCN program (15 and older) participants who can take responsibility for their health needs at school or work
K. | Percentage of CYSHCN program (15 and older) participants who can follow medical directons
L. | Percentage of CYSHCN program (15 and older) participants who have plans where to live as an adult
M. | Percentage of CYSHCN program (15 and older) participants who can arrange transportation
N. | Percentage of CYSHCN program (15 and older) participants who have information about school or tech training
O. | Percentage of CYSHCN program (15 and older) participants who have skills to live independently
P. | Percentage of CYSHCN physician who always or usually report that the treatment plan addresses youth development in assuming personal care/management and transition planning to adult medical providers?
SPM #9 | YSHCN whose doctors usually or always encourage development of age appropriate self management skills - National CSHCN survey
| Activities/Action Steps | Completion Date for Activity | Responsible Party
2.1 | Enhance community partnerships by identifying community resources, integrating service delivery systems, and streamlining the transition process for children and youth. |  | Heather Moore
2.1.1 | Identify available local, regional, state, and national resources.
OUTPUT | (1) Develop and disseminate a regional and state-wide resource tool kit and navigational guide. Provide maintenance and updates as necessary. (2) MADIN utilized to help improve linkages and collaboration with regard to transition services. | (1) Current and ongoing: Monitor what is being presented by national, state, and local partners. (1a) Begin development of resource guide by July 2010. Monitor resources and update guide as necessary, ongoing. (1b) Disseminate resource guide by March 2011. (1c) Begin development of navigational tool to accompany guide by April 2011. (1d) Disseminated navigational tool by December 2011. Continuous and Ongoing: Work with community service providers and state agencies to develop, maintain, and disseminate both tools. (2) Current and Ongoing: Promote MADIN through local and state conferences and exhibit booths to increase awareness of resource and provide additional services to families. (2a) Work with MADIN to identify the best dissemination method and to gain knowledge of additional resources to include in the resources guide, beginning July 2010. (2b) Put resource guide and navigational tool kit on MADIN upon completion of products. (2c) Explore the possibility of expanding MADIN to make the resource guide an on-line, interactive tool. March 2012.
| Activities/Action Steps | Completion Date for Activity | Responsible Party
2.1.2 | Participate in and sponsor conferences, meetings, and other networking opportunities related to the transition process.
OUTPUT | (1) Coordinate multi-state collaborative conference on health care transition. (2) Serve on stakeholder groups (3) Expand program advisory councils as appropriate to promote further integration and collaboration. (4) Participate and support other transition-related events and activities. | (1a) Serve on planning work group, April 2010. (1b) Co-host transition and medical home collaborative, Summer 2011. (1c) Evaluate and assess the benefit of the collaborative, Fall 2011. (1d) Determine, as a work group, if future collaboratives would be beneficial and how frequent they should occur, upon analysis of collaborative (Fall 2011) (2) Current and ongoing (3) Current and ongoing (4) Current and ongoing
2.2 | Inform and educate children, youth, and families about available transition services and where/how to access these services. |  | Heather Moore
2.2.1 | Identify available local, regional, state, and national resources.
OUTPUT | (1) Develop and disseminate a regional and state-wide resource tool kit and navigational guide. Provide maintenance and updates as necessary. (2) MADIN utilized to help improve linkages and collaboration with regard to transition services. | See Activity 2.1.1 Activity Timeline
| Activities/Action Steps | Completion Date for Activity | Responsible Party
2.2.2 | Promote successful transition through educational opportunities and self-advocacy training.
OUTPUT | (1) Recruit and maintain a Youth Advisory Council and provide opportunities to enhance leadership and self-advocacy skills. (2) Provide learning opportunities for families, youth, and partners on all aspects of transition. (3) Promote self-determination in transition planning through the use of a curriculum or planning instrument. | (1a) Develop YAC recruitment materials by May 2010. Recruitment begins May 2010 and ongoing. (1b) Host quarterly activities/meetings for council members and provide leadership and self-advocacy training, beginning August 2010 and ongoing. (2) Work with community partners to host, sponsor, or conduct trainings on the importance of health in transition, beginning July 2010 and ongoing. Through a partnership with KUCDD: (3a) develop curriculum (by July 2010), (3b) pilot curriculum in high schools (August 2010 - May 2011), (3c) evaluate (May - July 2011), (3d) disseminate to wider audience (August 2011 and ongoing).
2.2.3 | Identify, assess, and disseminate informatino and materials from local, regional, state, and national transition initiatives.
OUTPUT | (1) Transition initiatives and supporting information disseminated through CYSHCN and partner publications. (2) Develop transition materials, as needed, to disseminate to providers, families, and partners. | (1) Develop/disseminate articles about medical home for internal publications (e.g., CYSHCN magazine, column to newsletter), starting Summer 2010. (2) Develop/disseminate template articles and information for distribution through partner publications by June 2011.
PRIORITY #3: Financing for CYSHCN services minimizes financial hardship for their families.
Indicator(s) for Priority Objective #3
A. | Percentage CYSHCN whose families pay $1,000 or more out-of-pocket |  |  | Other indicators selected during small group work
B. | Percentage CYSHCN whose conditions cause financial problems for family
C. | Percentage CYSHCN whose families spend 11 or more hours a week providing health care
D. | Percentage CYSHCN whose conditions cause family members cut back or stopped working
E. | Percentage CSHCN (0-5 years) Parents who report at least one child care or employment issues
F. | Percentage CSHCN (0-5 years) Parents who report childcare effects employment
G. | Percentage CSHCN (0-5 years) Parents who made different arrangements for child care at the last minute due to circumstances beyond your control and had no problems
H. | Percentage CSHCN (6-11 years) who spends some time alone
I. | Percentage CYSHCN who have inadequate insurance
J. | Percentage CYSHCN have inadequate insurance
K. | Percentage CYSHCN parents whose out-of-pocket expenses are never or sometimes reasonable
SPM #10 | Percent of CSHCN families that experience financial problems due to the child's health needs - National CSHCN Survey
| Activities/Action Steps | Completion Date for Activity | Responsible Party
3.1 | Link families to providers who are contracted with or referred by the CYSHCN program and accept negotiated reimbursement rates. |  | Marc Shiff
3.1.1 | Monitor, assess, and evaluate federal and state policies as they relate to health coverage and services. | (1) Regular updates: as available and ongoing
OUTPUTS | (1) Information and updates are disseminated on websites, in newsletters, and other publications. (2) Regular updates are provided at internal and community meetings identifying anticipated impact on coverage and services. (3) Workshop(s), training(s), and materials are offered informing partners in how to advocate and change policy. (4) Kansas services and coverage's are benchmarked in relation to other states and peer groups. | (1) Info & updates: First product by Dec 2011 and ongoing (2) Regular updates: As available and ongoing (3) Trainings and workshops: Beginning year 3 (2013) (4) By July, 2011 and ongoing
| Activities/Action Steps | Completion Date for Activity | Responsible Party
3.1.2 | Provider outreach and education | (1) Regular updates: as available and ongoing
OUTPUTS | (1) See 3.1.1 outputs above, as applicable (2) CYSHCN program collects and provides Kansas-specific information on barriers and challenges to state and national professional and stakeholder organizations. (3) The impact of national and state professional organization recommendations on Kansas is assessed; appropriate information is disseminated to providers. | (1) See dates on 3.1.1, as applicable (2) Develop and Distribute Survey by July 2011 Collect by Dec 2011 Finalized report available by July 2012 Provide results and distribute - start July 2012 and ongoing Utilize in trainings/workshops - 2013 Ongoing informal communication with providers and state/national organizations, as appropriate (3) Monitor, and assess key recommendations within 4 months after release and disseminate information to providers, as appropriate
3.1.3 | Staff and Consumer education | (1) Regular updates: as available and ongoing
OUTPUTS | See 3.1.1 Outputs
3.1.4 | Educate and mobilize Families Together, Family Advisory Council, and other partners and stakeholder groups. | (1) Regular updates: as available and ongoing
OUTPUTS | See 3.1.1 Outputs
| Activities/Action Steps | Completion Date for Activity | Responsible Party
3.2 | Ensure CYSHCN Clinic/Field staff assist families in applying for and maximizing benefit of funding sources and family supports. |  | Marc Shiff
3.2.1 | Staff education
OUTPUTS | (1) Regular updates are provided at internal meetings identifying anticipated impact of health reform on coverage and services. (2) Staff monitors listservs, KS-Train, national resources to stay current. (3) Staff receives training and information on cultural competency/preferences. | (1 - 3) Regular updates: as available and ongoing (2)
3.2.2 | Identify, assess, and monitor resources at the state and local level. | (1) Regular updates: ongoing resource assessment and monitoring
OUTPUTS | Regular, ongoing communication regarding resources takes place among staff. | (1) Regular updates: Staff communication and updates occur monthly
3.3 | Support expansion of primary and specialty care services to minimize travel time and missed work/school days. |  | Marc Shiff
3.3.1 | Needs assessment of primary and specialty care services, current utilization, and gaps to service delivery | (1) An assessment of primary and specialty care services and utilization by January 2011
OUTPUTS | (1) Explore service expansion options, including alternative and innovative solutions (2) Regional specialty clinic implementation plan developed | (1) Service expansion options developed by July 2011 (2) Specialty clinic implementation plan developed by February 2012

## Glossary
Glossary of Terms and Acronyms
AAP | - American Academy of Pediatrics
ABCD+ | - Assure Better Child Development Plus; group formed to improved mental health screening, referral and resources
ATOD | - Alcohol, Tobacco, or Other Drugs
BFH | - Bureau of Family Health
breastfeeding dyad | - A breastfeeding mother and her breastfed infant(s)
Business Case for Breastfeeding | - Program designed to educate employers about the value of supporting breastfeeding employees in the workplace
BRFSS | -Behavior Risk Factor Surveillance System
C&A | - Children and Adolescents
CDC-DASH | - Center for Disease Control and Prevention - Division of Adolescent and School Health
CSHCN | - Children with Special Health Care Needs
CYSHCN | - Children and Youth with Special Health Care Needs
EC | - Early Childhood; generally the period from birth through age 5
Healthy Families | - Services funded in part by the Kansas Medicaid program of intensive case management for high-risk pregnant women
IMR | - Infant Mortality Rate
KALHD | - Kansas Associate of Local Health Departments
KDHE | - Kansas Department of Health and Environment
KHI | - Kansas Health Institute
KHPA | - Kansas Health Policy Authority
KS-TRAIN | - TrainingFinder Real-time Affiliate Integrated Network; a learning resource for professionals to protect public health and safety
LBW | - Low Birth Weight
Loving Support | - A breastfeeding promotional campaign
MCH | - Maternal and Child Health
MCH 2015 | - Needs assessment and health planning process improving Kansas' care of women and children
MOA | - Memorandum of Agreement
MOD | - March of Dimes
PRAMS | - Pregnancy Risk Assessment Monitoring System
SPM | - State Performance Measure
text4baby | - A mobile information service designed to promote maternal and child health
W&I | - Pregnant Women and Infants
WIC | - Women, Infants, and Children
YRBSS | - Youth Risk Behavior Surveillance System
YSHCN | - Youth with Special Health Care Needs