## Instructions
Logic Model Instructions:
Note: | Remember to consider stakeholder input from meetings one and two when finalizing Strategies and Action Steps.
(1) Strategies: To be completed by Section Directors.
(a) For each priority, enter strategies in bright yellow cells. List up to 3 strategies for each priority. Strategies will stay the same over the next five years.
(b) Select corresponding Essential MCH Service from drop-down list in pale blue cell.
(2) Logic Model Table for each strategy: To be completed by Staff at the March 26th meeting.
Note: As you are developing action steps and listing outputs, keep in mind the end goal, the long-term outcome.
(a) For each strategy, enter action steps in pale orange cells. List up to 3 activities/action steps per strategy. Activities / action steps may change over the five years.
(b) Enter outputs, short-term outcomes, intermediate outcomes and long-term outcomes for each strategy. You do not necessarily need to have these for each action step; they may correspond to multiple (or all) action steps under a strategy.
Workplan Instructions:
(1) Enter the priority indicators in the lavendar cells. Select 1-3 indicators for each priority.
(2) Light gray dotted cells (like those at the left), with Activities/Action Steps and Strategies will fill in automatically from the Logic Model spreadsheets.
(3) Fill in Responsible Party (light green cell) for each Strategy, if desired.
(4) Enter the expected Completion Date or timeline for each actiivty.
(5) Enter the Responsible Part for each activity, if not entered at Strategy level or different than Strategy Responsible Party.

## M&I Logic Models
Mothers & Infants Logic Model
VISION - Healthy Children in Healthy Families |  | MISSION - Provide leadership to enhance the health of Kansas women and children in partnership with families and communities.
GOAL STATEMENT: To enhance the health of Kansas women and infants across the lifespan.
PRIORITY OBJECTIVE #1: All women receive early and comprehensive health care before, during and after pregancy.
Planned Activities/Action Steps |  | Outputs Immediate or by June 30, 2011 | Short-Term Outcomes by Dec. 31, 2011 | Intermediate Outcomes by Dec. 31, 2012 | Long-Term Outcomes by June 20, 2015
Strategy 1.1: Enter Strategy, Essential MCH Service, and Planned Activities below.
1.1 | Strategy: | Educate women and their male partners to understand and participate in reproductive health decisions that lead to a healthy pregnancy.
Essential MCH Service (select from list): |  | 3. Inform/educate the public/families about MCH issues
1.1.1
1.1.2
1.1.3
1.1.4
Strategy 1.2: Enter Strategy, Essential MCH Service, and Planned Activities below.
1.2 | Strategy: | Create a system of dissemination of information to health care providers regarding existing reproductive health resources and support services available.
Essential MCH Service (select from list): |  | 4. Mobilize community partnerships to solve MCH issues
1.2.1
1.2.2
1.2.3
1.2.4
Strategy 1.3: Enter Strategy, Essential MCH Service, and Planned Activities below.
1.3 | Strategy: | Provide risk reduction services and case management for pregnant women in securing reproductive medical care throughout Kansas.
Essential MCH Service (select from list): |  | 7. Link women & children with services and assure quality systems of care
1.3.1
1.3.2
1.3.3
1.3.4
PRIORITY OBJECTIVE #2: Improve mental health and behavioral health of pregnant women and new mothers.
Planned Activities/Action Steps |  | Outputs Immediate or by June 30, 2011 | Short-Term Outcomes by Dec. 31, 2011 | Intermediate Outcomes by Dec. 31, 2012 | Long-Term Outcomes by June 20, 2015
Strategy 2.1: Enter Strategy, Essential MCH Service, and Planned Activities below.
2.1 | Strategy: | Implement a public awareness campaign to recognize mental health and behavioral health impacts of a healthy pregnancy.
Essential MCH Service (select from list): |  | 3. Inform/educate the public/families about MCH issues
2.1.1
2.1.2
2.1.3
2.1.4
Strategy 2.2: Enter Strategy, Essential MCH Service, and Planned Activities below.
2.2 | Strategy: | Advocate for policy change to implement universal mental health and behavioral health screening for all pregnant women and mothers in Kansas.
Essential MCH Service (select from list): |  | 5. Leadership in setting priorities, planning and policy development
2.2.1
2.2.2
2.2.3
2.2.4
Strategy 2.3: Enter Strategy, Essential MCH Service, and Planned Activities below.
2.3 | Strategy: | Educate and provide evidence based tools for diagnosing mood disorders, substance abuse, intimate partner violence , and sexual assalt to health care providers and public health workforce.
Essential MCH Service (select from list): |  | 8. Assure work force capacity and competency
2.3.1
2.3.2
2.3.3
2.3.4
PRIORITY OBJECTIVE #3: Reduce preterm and low birthweight births, and infant mortality.
Planned Activities/Action Steps |  | Outputs Immediate or by June 30, 2011 | Short-Term Outcomes by Dec. 31, 2011 | Intermediate Outcomes by Dec. 31, 2012 | Long-Term Outcomes by June 20, 2015
Strategy 3.1: Enter Strategy, Essential MCH Service, and Planned Activities below.
3.1 | Strategy: | Partner to educate the public and health providers on issues related to contributing factors leading to preterm birth, low-birth weight, and infant mortality.
Essential MCH Service (select from list): |  | 4. Mobilize community partnerships to solve MCH issues
3.1.1
3.1.2
3.1.3
3.1.4
Strategy 3.2: Enter Strategy, Essential MCH Service, and Planned Activities below.
3.2 | Strategy: | Educate reproductive health providers and the public health workforce on best practice for prenatal risk assessment of all women of reproductive age.
Essential MCH Service (select from list): |  | 8. Assure work force capacity and competency
3.2.1
3.2.2
3.2.3
3.2.4
Strategy 3.3: Enter Strategy, Essential MCH Service, and Planned Activities below.
3.3 | Strategy: | Direct targeted funding to provide comprehensive outreach and support services to pregnant women of racial and ethnic minorities.
Essential MCH Service (select from list): |  | 10. Support research and demonstration projects
3.3.1
3.3.2
3.3.3
3.3.4
PRIORITY OBJECTIVE #4: Increase initiation, duration and exclusivity of breastfeeding.
Planned Activities/Action Steps |  | Outputs Immediate or by June 30, 2011 | Short-Term Outcomes by Dec. 31, 2011 | Intermediate Outcomes by Dec. 31, 2012 | Long-Term Outcomes by June 20, 2015
Strategy 4.1: Enter Strategy, Essential MCH Service, and Planned Activities below.
4.1 | Strategy: | Educate Kansans on the benefits of breastfeeding infants exclusively for the first six months.
Essential MCH Service (select from list): |  | 3. Inform/educate the public/families about MCH issues
4.1.1
4.1.2
4.1.3
4.1.4
Strategy 4.2: Enter Strategy, Essential MCH Service, and Planned Activities below.
4.2 | Strategy: | Collaborate with hospitals and employers to adapt policies to support initiation and continuation of breastfeeding infants.
Essential MCH Service (select from list): |  | 4. Mobilize community partnerships to solve MCH issues
4.2.1
4.2.2
4.2.3
4.2.4
Strategy 4.3: Enter Strategy, Essential MCH Service, and Planned Activities below.
4.3 | Strategy: | Provide education and training of health care providers and public health workforce in comprehensive lactation support services.
Essential MCH Service (select from list): |  | 8. Assure work force capacity and competency
4.3.1
4.3.2
4.3.3
4.3.4

## M&I Workplan
Mothers & Infants Workplan
VISION - Healthy Children in Healthy Families
MISSION - Provide leadership to enhance the health of Kansas women and children in partnership with families and communities.
GOAL STATEMENT: To enhance the health of Kansas women and infants across the lifespan.
PRIORITY OBJECTIVE #1: All women receive early and comprehensive health care before, during and after pregnancy.
| Indicator(s) for Priority Objective #1 |  | *Source:
1. | Percentage of women who currently have some type of health care coverage (ages 18-44) |  | BRFSS
| Activities/Action Steps | Completion Date for Activity | Responsible Party
1.1 | Educate women and their male partners to understand and participate in reproductive health decisions that lead to a healthy pregnancy. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
1.2 | Create a system of dissemination of information to health care providers regarding existing reproductive health resources and support services available. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
1.3 | Provide risk reduction services and case management for pregnant women in securing reproductive medical care throughout Kansas. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
PRIORITY #2: Improve mental health and behavioral health of pregnant women and new mothers.
| Indicator(s) for Priority Objective #2 |  | *Source:
1. | Percentage of women who report that their mental health was not good for at least 14 out of the past 30 days (ages 18-44) |  | BRFSS
2. | Percentage of women having a live birth who smoked cigarettes during pregnancy |  | Birth Certificate / PNSS
3. | Percentage of women having a live births who drank 3 months prior to pregnancy |  | PNSS
| Activities/Action Steps | Completion Date for Activity | Responsible Party
2.1 | Implement a public awareness campaign to recognize mental health and behavioral health impacts of a healthy pregnancy. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
2.2 | Advocate for policy change to implement universal mental health and behavioral health screening for all pregnant women and mothers in Kansas. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
2.3 | Educate and provide evidence based tools for diagnosing mood disorders, substance abuse, intimate partner violence , and sexual assalt to health care providers and public health workforce. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
PRIORITY #3: Reduce preterm and low birthweight births, and infant mortality.
| Indicator(s) for Priority Objective #3 |  | *Source:
1. | Percentage of total preterm births (<37 weeks) · Percentage of live briths at 34 to 36 weeks of gestation (late preterm) · Percentage of live births at <32 weeks of gestation (very premature) |  | Birth Certificate
| Activities/Action Steps | Completion Date for Activity | Responsible Party
3.1 | Partner to educate the public and health providers on issues related to contributing factors leading to preterm birth, low-birth weight, and infant mortality. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
3.2 | Educate reproductive health providers and the public health workforce on best practice for prenatal risk assessment of all women of reproductive age. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
3.3 | Direct targeted funding to provide comprehensive outreach and support services to pregnant women of racial and ethnic minorities. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
PRIORITY #4: Increase initiation, duration and exclusivity of breastfeeding.
| Indicator(s) for Priority Objective #4 |  | *Source:
1. | Percentage of Kansas WIC infants breastfed at least 6 months |  | PedNSS
| Activities/Action Steps | Completion Date for Activity | Responsible Party
4.1 | Educate Kansans on the benefits of breastfeeding infants exclusively for the first six months. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
4.2 | Collaborate with hospitals and employers to adapt policies to support initiation and continuation of breastfeeding infants. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
4.3 | Provide education and training of health care providers and public health workforce in comprehensive lactation support services. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
*Note: All sources available annually

## C&A Logic Models
Children & Adolescents Logic Model
VISION - Healthy Children in Healthy Families |  | MISSION - Provide leadership to enhance the health of Kansas women and children in partnership with families and communities.
GOAL STATEMENT: To enhance the health of children and adolescents across the lifespan.
PRIORITY OBJECTIVE #1: All children and youth receive health care through medical homes.
Planned Activities/Action Steps |  | Outputs Immediate or by June 30, 2011 | Short-Term Outcomes by Dec. 31, 2011 | Intermediate Outcomes by Dec. 31, 2012 | Long-Term Outcomes by June 20, 2015
Strategy 1.1: Enter Strategy, Essential MCH Service, and Planned Activities below.
1.1 | Strategy: | Enlist the assistance of community partners to increase Medicaid/HealthWave enrollment for eligible children.
Essential MCH Service (select from list): |  | 4. Mobilize community partnerships to solve MCH issues
1.1.1
1.1.2
1.1.3
1.1.4
Strategy 1.2: Enter Strategy, Essential MCH Service, and Planned Activities below.
1.2 | Strategy: | Educate parents on medical home concept and navigation of health system for health care services.
Essential MCH Service (select from list): |  | 3. Inform/educate the public/families about MCH issues
1.2.1
1.2.2
1.2.3
1.2.4
Strategy 1.3: Enter Strategy, Essential MCH Service, and Planned Activities below.
1.3 | Strategy: | Assure that local health departments have community / regional health services and information available to the public including medical, mental health, and dental health.
Essential MCH Service (select from list): |  | 7. Link women & children with services and assure quality systems of care
1.3.1
1.3.2
1.3.3
1.3.4
PRIORITY OBJECTIVE #2: Mobilize community partners and stakeholders to reduce risky behavior among children and youth ages 1-21.
Planned Activities/Action Steps |  | Outputs Immediate or by June 30, 2011 | Short-Term Outcomes by Dec. 31, 2011 | Intermediate Outcomes by Dec. 31, 2012 | Long-Term Outcomes by June 20, 2015
Strategy 2.1: Enter Strategy, Essential MCH Service, and Planned Activities below.
2.1 | Strategy: | Identify geographical areas of risky behavior to target interventions.
Essential MCH Service (select from list): |  | 1. Assess/monitor health status of women and children to ID/address problems
2.1.1
2.1.2
2.1.3
2.1.4
Strategy 2.2: Enter Strategy, Essential MCH Service, and Planned Activities below.
2.2 | Strategy: | Coordinate efforts within the state to address risky behavior.
Essential MCH Service (select from list): |  | 4. Mobilize community partnerships to solve MCH issues
2.2.1
2.2.2
2.2.3
2.2.4
Strategy 2.3: Enter Strategy, Essential MCH Service, and Planned Activities below.
2.3 | Strategy: | Promote use of comprehensive health education provided by public and private organizations serving children and youth.
Essential MCH Service (select from list): |  | 4. Mobilize community partnerships to solve MCH issues
2.3.1
2.3.2
2.3.3
2.3.4
Strategy 2.4: Enter Strategy, Essential MCH Service, and Planned Activities below.
2.4 | Strategy: | Educate and inform all state level agencies serving families about programs and initiatives to reduce risky behavior in children and youth.
Essential MCH Service (select from list): |  | 5. Leadership in setting priorities, planning and policy development
2.4.1
2.4.2
2.4.3
2.4.4
PRIORITY OBJECTIVE #3: All children and youth achieve and maintain healthy weight.
Planned Activities/Action Steps |  | Outputs Immediate or by June 30, 2011 | Short-Term Outcomes by Dec. 31, 2011 | Intermediate Outcomes by Dec. 31, 2012 | Long-Term Outcomes by June 20, 2015
Strategy 3.1: Enter Strategy, Essential MCH Service, and Planned Activities below.
3.1 | Strategy: | Promote standardization of health provider practice to include at a minimum, an annual BMI assessment on all Kansas children ages 2 – 18.
Essential MCH Service (select from list): |  | 1. Assess/monitor health status of women and children to ID/address problems
3.1.1
3.1.2
3.1.3
3.1.4
Strategy 3.2: Enter Strategy, Essential MCH Service, and Planned Activities below.
3.2 | Strategy: | Identify and implement strategies to address childhood obesity.
Essential MCH Service (select from list): |  | 5. Leadership in setting priorities, planning and policy development
3.2.1
3.2.2
3.2.3
3.2.4
Strategy 3.3: Enter Strategy, Essential MCH Service, and Planned Activities below.
3.3 | Strategy: | Assure that local health departments have training on best practices in the identification, treatment and prevention of obesity.
Essential MCH Service (select from list): |  | 8. Assure work force capacity and competency
3.3.1
3.3.2
3.3.3
3.3.4

## C&A Workplan
Children & Adolescents Workplan
VISION - Healthy Children in Healthy Families
MISSION - Provide leadership to enhance the health of Kansas women and children in partnership with families and communities.
GOAL STATEMENT: To enhance the health of children and adolescents across the lifespan.
PRIORITY OBJECTIVE #1: All children and youth receive health care through medical homes.
Indicator(s) for Priority Objective #1
Medical Home1
A. | Percentage of children who receive care in medical home as defined by AAP
B. | Percentage of children aged 2-17 with problems requiring counseling who received mental health care
C. | Percentage of children who receive BOTH routine preventive medical and dental care visits
D. | Percentage of children who had at least one unmet medical need
E. | Percentage of children in excellent or good health
F. | Percentage of children with excellent or very good oral health
G. | Percentage of children aged 1-17 who at least one oral health problem in past 6 months
| Activities/Action Steps | Completion Date for Activity | Responsible Party
1.1 | Enlist the assistance of community partners to increase Medicaid/HealthWave enrollment for eligible children. |  |  | TRUE
FALSE
FALSE
FALSE
| Activities/Action Steps | Completion Date for Activity | Responsible Party
1.2 | Educate parents on medical home concept and navigation of health system for health care services. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
1.3 | Assure that local health departments have community / regional health services and information available to the public including medical, mental health, and dental health. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
PRIORITY #2: Mobilize community partners and stakeholders to reduce risky behavior among children and youth ages 1-21.
Indicator(s) for Priority Objective #2
Tobacco use2
A. | Percentage of students had smoked cigarettes on at least 1 day during the 30 days before the survey
B. | Percentage of students had used smokeless tobacco (e.g., chewing tobacco, snuff, or dip) on at least 1 day during the 30 days before the survey
C. | Percentage of students had smoked a whole cigarette for the first time before age 13 years
D. | Percentage of students had smoked cigarettes on school property on at least 1 day during the 30 days before the survey
Alcohol and other drug use2
A. | Percentage of students had had at least one drink of alcohol on at least 1 day during their life and 44.7% of students had had at least one drink of alcohol on at least 1 day during the 30 days before the survey
B. | Percentage of students had drunk alcohol (other than a few sips) for the first time before age 13 years
C. | Percentage of students had had five or more drinks of alcohol in a row (i.e., within a couple of hours) on at least 1 day during the 30 days before the survey
D. | Percentage of students had used marijuana one or more times during their life
E. | Percentage of students had used marijuana one or more times during the 30 days before the survey
F. | Percentage of students had tried marijuana for the first time before age 13 years
G. | Percentage of students had used any form of cocaine (e.g., powder, crack, or freebase ) one or more times during the 30 days before the survey
H. | Percentage of students had sniffed glue, breathed the contents of aerosol spray cans, or inhaled any paints or sprays to get high one or more times during their life
| Activities/Action Steps | Completion Date for Activity | Responsible Party
2.1 | Identify geographical areas of risky behavior to target interventions. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
2.2 | Coordinate efforts within the state to address risky behavior. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
| Activities/Action Steps | Completion Date for Activity | Responsible Party
2.3 | Promote use of comprehensive health education provided by public and private organizations serving children and youth. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
2.4 | Educate and inform all state level agencies serving families about programs and initiatives to reduce risky behavior in children and youth. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
PRIORITY #3: All children and youth achieve and maintain healthy weight.
Indicator(s) for Priority Objective #3
Physical Inactivity2
A. | Percentage of students met recommended levels of physical activity by being physically active doing any kind of physical activity that increased their heart rate and made them breathe hard some of the time for a total of at least 60 minutes per day on 5 or more days during the 7 days before the survey
B. | Percentage of students went to physical education (PE) classes on 1 or more days in an average week when they were in school and 30.3% of students went to PE classes 5 days in an average week when they were in school
C. | Percentage of students played video or computer games or used a computer for something that was not school work for 3 or more hours per day on an average school day
D. | Percentage of students watched television 3 or more hours per day on an average school day
Obesity and Dietary Behaviors2
A. | Percentage of students were obese
B. | Percentage of students were overweight
C. | Percentage of students had eaten fruits and vegetables five or more times per day during the 7 days before the survey
D. | Percentage of students had drunk a can, bottle, or glass of soda or pop (not including diet soda or diet pop) at least one time per day during the 7 days before the survey
E. | Percentage of students did not eat for 24 or more hours; took diet pills, powders, or liquids; or vomited or took laxatives to lose weight or to keep from gaining weight during the 30 days before the survey
Kansas WIC Children3
A. | Percentage of obesity in children aged <5 years
B. | Percentage of overweight in children aged <5 years
C. | Percentage of obesity in children aged 2 to <5 years
D. | Percentage of overweight in children aged 2 to <5 years
E. | Percentage of children aged 2 to <5 years viewed 2 hours of less of television per day.
| Activities/Action Steps | Completion Date for Activity | Responsible Party
3.1 | Promote standardization of health provider practice to include at a minimum, an annual BMI assessment on all Kansas children ages 2 – 18. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
3.2 | Identify and implement strategies to address childhood obesity. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
| Activities/Action Steps | Completion Date for Activity | Responsible Party | TRUE
3.3 | Assure that local health departments have training on best practices in the identification, treatment and prevention of obesity. |  |  | FALSE
FALSE
FALSE
FALSE
1 | HRSA Nation Survey of Child Health
2 | Data Source: YRBSS - The YRBSS is conducted every two years during the spring semester and provides data representative of 9th through 12th grade students in public and private schools.
3 | Data Source: PedNSS

## C&A Indicators
Children & Adolescents Indicators
Priority #1: All children and youth receive health care through medical homes
Medical Home | Indicators | KS Measure | Year | Data Source
| % of children who receive care in medical home as defined by AAP | 61.3 | 2007 | HRSA. Nation Survey of Child Health
| % of children aged 2-17 with problems requiring counseling who received mental health care | 72.3 | 2007 | HRSA. Nation Survey of Child Health
| % of children who receive BOTH routine preventive medical and dental care visits? | 73.9 | 2007 | HRSA. Nation Survey of Child Health
| % of children who had at least one unmet medical need | 5.7 | 2007 | HRSA. Nation Survey of Child Health
| % of children in excellent or good health | 85.3 | 2007 | HRSA. Nation Survey of Child Health
| % of children with excellent or very good oral health | 71.3 | 2007 | HRSA. Nation Survey of Child Health
| % of children aged 1-17 who at least one oral health problem in past 6 months | 23.7 | 2007 | HRSA. Nation Survey of Child Health
Priority #2: Mobilize community partners and stakeholders to reduce risky behavior among children and youth ages 1-21.
| Indicators | Data Source
Tobacco use | Percentage of students had smoked cigarettes on at least 1 day during the 30 days before the survey | YRBSS*
| Percentage of students had used smokeless tobacco (e.g., chewing tobacco, snuff, or dip) on at least 1 day during the 30 days before the survey | YRBSS
| Percentage of students had smoked a whole cigarette for the first time before age 13 years | YRBSS
| Percentage of students had smoked cigarettes on school property on at least 1 day during the 30 days before the survey | YRBSS
* YRBSS is conducted every two years during the spring semester and provides data representative of 9th through 12th grade students in public and private schools.
| Indicators | Data source
Alcohol and other drug use | Percentage of students had had at least one drink of alcohol on at least 1 day during their life and 44.7% of students had had at least one drink of alcohol on at least 1 day during the 30 days before the survey | YRBSS
| Percentage of students had drunk alcohol (other than a few sips) for the first time before age 13 years | YRBSS
| Percentage of students had had five or more drinks of alcohol in a row (i.e., within a couple of hours) on at least 1 day during the 30 days before the survey | YRBSS
| Percentage of students had used marijuana one or more times during their life | YRBSS
| Percentage of students had used marijuana one or more times during the 30 days before the survey | YRBSS
| Percentage of students had tried marijuana for the first time before age 13 years | YRBSS
| Percentage of students had used any form of cocaine (e.g., powder, crack, or freebase ) one or more times during the 30 days before the survey | YRBSS
| Percentage of students had sniffed glue, breathed the contents of aerosol spr ay cans, or inhaled any paints or sprays to get high one or more times during their life | YRBSS
Priority #3: All children and youth achieve and maintain healthy weight
| Indicators | Data source
Physical Inactivity | Percentage of students met recommended levels of physical activity by being physically active doing any kind of physical activity that increased their heart rate and made them breathe hard some of the time for a total of at least 60 minutes per day on 5 or more days during the 7 days before the survey | YRBSS
| Percentage of students went to physical education (PE) classes on 1 or more days in an average week when they were in school and 30.3% of students went to PE classes 5 days in an average week when they were in school | YRBSS
| Percentage of students played video or computer games or used a computer for something that was not school work for 3 or more hours per day on an average school day | YRBSS
| Percentage of students watched television 3 or more hours per day on an average school day | YRBSS
| Indicators | Data source
Obesity and Dietary Behaviors | Percentage of students were obese | YRBSS
| Percentage of students were overweight | YRBSS
| Percentage of students had eaten fruits and vegetables five or more times per day during the 7 days before the survey | YRBSS
| Percentage of students had drunk a can, bottle, or glass of soda or pop (not including diet soda or diet pop) at least one time per day during the 7 days before the survey | YRBSS
| Percentage of students did not eat for 24 or more hours; took diet pills, powders, or liquids; or vomited or took laxatives to lose weight or to keep from gaining weight during the 30 days before the survey | YRBSS
| Indicators | Data source
Kansas WIC Children | Percentage of obesity in children aged <5 years | PedNSS
| Percentage of overweight in children aged <5 years | PedNSS
| Percentage of obesity in children aged 2 to <5 years | PedNSS
| Percentage of overweight in children aged 2 to <5 years | PedNSS
| Percentage of children aged 2 to <5 years viewed 2 hours of less of television per day. | PedNSS

## CYSHCN Logic Models
Children & Youth with Special Health Care Needs Logic Model
VISION - Healthy Children in Healthy Families |  | MISSION - Provide leadership to enhance the health of Kansas women and children in partnership with families and communities.
GOAL STATEMENT: To enhance the health of all children and and youth with special health care needs across the lifespan.
PRIORITY OBJECTIVE #1: All CYSHCN receive coordinated, comprehensive care within a medical home.
Planned Activities/Action Steps |  | Outputs Immediate or by June 30, 2011 | Short-Term Outcomes by Dec. 31, 2011 | Intermediate Outcomes by Dec. 31, 2012 | Long-Term Outcomes by June 20, 2015
Strategy 1.1: Enter Strategy, Essential MCH Service, and Planned Activities below.
1.1 | Strategy: | Mobilize community partnerships (between policy makers, health care providers, families, and the public) by coordinating services for eligible CYSHCN identified through Newborn Screening and linking children and families to providers and community services/resources.
Essential MCH Service (select from list): |  | 4. Mobilize community partnerships to solve MCH issues
1.1.1
1.1.2
1.1.3
1.1.4
Strategy 1.2: Enter Strategy, Essential MCH Service, and Planned Activities below.
1.2 | Strategy: | Inform, educate, and involve families and providers about medical home components and initiatives to promote effective and successful systems change.
Essential MCH Service (select from list): |  | 3. Inform/educate the public/families about MCH issues
1.2.1
1.2.2
1.2.3
1.2.4
Strategy 1.3: Enter Strategy, Essential MCH Service, and Planned Activities below.
1.3 | Strategy:
Essential MCH Service (select from list): |  | <None Selected>
1.3.1
1.3.2
1.3.3
1.3.4
PRIORITY OBJECTIVE #2: CYSHCN receive services necessary to make transitions to all aspects of adult life, including adult health care, work and independence.
Planned Activities/Action Steps |  | Outputs Immediate or by June 30, 2011 | Short-Term Outcomes by Dec. 31, 2011 | Intermediate Outcomes by Dec. 31, 2012 | Long-Term Outcomes by June 20, 2015
Strategy 2.1: Enter Strategy, Essential MCH Service, and Planned Activities below.
2.1 | Strategy: | Enhance community partnerships by identifying community resources, integrating service delivery systems, and streamlining the transition process for children and youth.
Essential MCH Service (select from list): |  | 4. Mobilize community partnerships to solve MCH issues
2.1.1
2.1.2
2.1.3
2.1.4
Strategy 2.2: Enter Strategy, Essential MCH Service, and Planned Activities below.
2.2 | Strategy: | Inform and educate children and youth about available transition services and where/how to access these services.
Essential MCH Service (select from list): |  | 7. Link women & children with services and assure quality systems of care
2.2.1
2.2.2
2.2.3
2.2.4
Strategy 2.3: Enter Strategy, Essential MCH Service, and Planned Activities below.
2.3 | Strategy:
Essential MCH Service (select from list): |  | <None Selected>
2.3.1
2.3.2
2.3.3
2.3.4
PRIORITY OBJECTIVE #3: Financing for CYSHCN services minimizes financial hardship for their families.
Planned Activities/Action Steps |  | Outputs Immediate or by June 30, 2011 | Short-Term Outcomes by Dec. 31, 2011 | Intermediate Outcomes by Dec. 31, 2012 | Long-Term Outcomes by June 20, 2015
Strategy 3.1: Enter Strategy, Essential MCH Service, and Planned Activities below.
3.1 | Strategy: | Link families to CYSHCN providers who are contracted with CYSHCN and accept negotiated reimbursement rates.
Essential MCH Service (select from list): |  | 7. Link women & children with services and assure quality systems of care
3.1.1
3.1.2
3.1.3
3.1.4
Strategy 3.2: Enter Strategy, Essential MCH Service, and Planned Activities below.
3.2 | Strategy: | Ensure CYSHCN Clinic/Field staff assist families in applying for possible funding sources.
Essential MCH Service (select from list): |  | 9. Evaluate effectiveness, accessibility, quality
3.2.1
3.2.2
3.2.3
3.2.4
Strategy 3.3: Enter Strategy, Essential MCH Service, and Planned Activities below.
3.3 | Strategy: | Support expansion of primary and specialty care services to minimize travel time and missed work/school days.
Essential MCH Service (select from list): |  | 5. Leadership in setting priorities, planning and policy development
3.3.1
3.3.2
3.3.3
3.3.4

## CYSHCN Workplan
Children & Youth with Special Health Care Needs Workplan
VISION - Healthy Children in Healthy Families
MISSION - Provide leadership to enhance the health of Kansas women and children in partnership with families and communities.
GOAL STATEMENT: To enhance the health of all children and youth with special health care needs across the lifespan.
PRIORITY OBJECTIVE #1: All CYSHCN receive coordinated, comprehensive care within a medical home.
Indicator(s) for Priority Objective #1
A. | Percentage of CYSHCN who receive care in medical home as defined by AAP
B. | Percentage of CYSHCN who receive care in medical home
C. | Percentage of CYSHCN aged 2-17 with problems requiring counseling who received mental health care
D. | Percentage of CYSHCN who receive BOTH routine preventive medical and dental care visits?
E. | Percentage of CYSHCN who had at least one unmet medical need
F. | Percentage of CYSHCN who have at least one need for specific health services
G. | Percentage of CYSHCN who have at least one need for family supportive services
H. | Percentage of CYSHCN who had difficulty getting a referral
I. | Percentage of CYSHCN who had difficulty getting a referral
J. | Percentage of CYSHCN aged 1-17 who at least one oral health problem in past 6 months
K. | Percentage of CYSHCN aged 6-17 who have medical, behavioral or other health conditions which interfere with their ability to attend school regularly, participate in sports or other activities, or make friends
| Activities/Action Steps | Completion Date for Activity | Responsible Party
1.1 | Mobilize community partnerships (between policy makers, health care providers, families, and the public) by coordinating services for eligible CYSHCN identified through Newborn Screening and linking children and families to providers and community services/resources. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
1.2 | Inform, educate, and involve families and providers about medical home components and initiatives to promote effective and successful systems change. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
1.3 |  |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
PRIORITY #2: CYSHCN receive services necessary to make transitions to all aspects of adult life, including adult health care, work and independence.
Indicator(s) for Priority Objective #2
A. | Percentage YSHCN (12-17 years) who receive the services necessary to make appropriate transitions to adult health care, work and independence
B. | Percentage of recipients successfully transition from Part C to Part B
C. | Percentage YSHCN receive all anticipatory guidance for transition to adult health care
D. | Percentage YSHCN whose doctors usually or always encourage development of age appropriate self management skills
E. | Percentage of CYSHCN program (15 and older) participants who found an adult doctor
F. | Percentage of CYSHCN program (15 and older) participants who found an adult specialist
G. | Percentage of CYSHCN program (15 and older) participants who know when to report changes in their health
H. | Percentage of CYSHCN program (15 and older) participants who know how to get emergency help
I. | Percentage of CYSHCN program (15 and older) participants who can take responsibility for their health needs at home
J. | Percentage of CYSHCN program (15 and older) participants who can take responsibility for their health needs at school or work
K. | Percentage of CYSHCN program (15 and older) participants who can follow medical directons
L. | Percentage of CYSHCN program (15 and older) participants who have plans where to live as an adult
M. | Percentage of CYSHCN program (15 and older) participants who can arrange transportation
N. | Percentage of CYSHCN program (15 and older) participants who have information about school or tech training
O. | Percentage of CYSHCN program (15 and older) participants who have skills to live independently
P. | Percentage of CYSHCN physician who always or usually report that the treatment plan addresses youth development in assuming personal care/management and transition planning to adult medical providers?
| Activities/Action Steps | Completion Date for Activity | Responsible Party
2.1 | Enhance community partnerships by identifying community resources, integrating service delivery systems, and streamlining the transition process for children and youth. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
2.2 | Inform and educate children and youth about available transition services and where/how to access these services. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
2.3 |  |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
PRIORITY #3: Financing for CYSHCN services minimizes financial hardship for their families.
Indicator(s) for Priority Objective #3
A. | Percentage CYSHCN whose families pay $1,000 or more out-of-pocket
B. | Percentage CYSHCN whose conditions cause financial problems for family
C. | Percentage CYSHCN whose families spend 11 or more hours a week providing health care
D. | Percentage CYSHCN whose conditions cause family members cut back or stopped working
E. | Percentage CSHCN (0-5 years) Parents who report at least one child care or employment issues
F. | Percentage CSHCN (0-5 years) Parents who report childcare effects employment
G. | Percentage CSHCN (0-5 years) Parents who made different arrangements for child care at the last minute due to circumstances beyond your control and had no problems
H. | Percentage CSHCN (6-11 years) who spends some time alone
I. | Percentage CYSHCN who have inadequate insurance
J. | Percentage CYSHCN have inadequate insurance
K. | Percentage CYSHCN parents whose out-of-pocket expenses are never or sometimes reasonable
| Activities/Action Steps | Completion Date for Activity | Responsible Party
3.1 | Link families to CYSHCN providers who are contracted with CYSHCN and accept negotiated reimbursement rates. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
3.2 | Ensure CYSHCN Clinic/Field staff assist families in applying for possible funding sources. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE
3.3 | Support expansion of primary and specialty care services to minimize travel time and missed work/school days. |  |  | TRUE
FALSE
FALSE
FALSE
FALSE

## CYSHCN Indicators
Children & Youth with Special Health Care Needs Indicators
PRIORITY OBJECTIVE #1: All CYSHCN receive coordinated, comprehensive care within a medical home.
Medical Home | Indicator | KS Measure | Year | Data Source
| Percentage of CYSHCN who receive care in medical home as defined by AAP | 49.3 | 2007 | HRSA. Nation Survey of Child Health
| Percentage of CYSHCN who receive care in medical home | 47.1 | 2005/2006 | HRSA. Nation Survey of CSHCN
| Percentage of CYSHCN aged 2-17 with problems requiring counseling who received mental health care | 71.6 | 2007 | HRSA. Nation Survey of Child Health
| Percentage of CYSHCN who receive BOTH routine preventive medical and dental care visits | 84.9 | 2007 | HRSA. Nation Survey of Child Health
| Percentage of CYSHCN who had at least one unmet medical need | 10.3 | 2007 | HRSA. Nation Survey of Child Health
| Percentage of CYSHCN who have at least one need for specific health services | 12 | 2005/2006 | HRSA. Nation Survey of CSHCN
| Percentage of CYSHCN who have at least one need for family supportive services | 3.2 | 2005/2006 | HRSA. Nation Survey of CSHCN
| Percentage of CYSHCN who had difficulty getting a referral | 11.4 | 2005/2006 | HRSA. Nation Survey of CSHCN
| Percentage of CYSHCN who had difficulty getting a referral | 12 | 2007 | HRSA. Nation Survey of Child Health
| Percentage of CYSHCN aged 1-17 who at least one oral health problem in past 6 months | 25.6 | 2007 | HRSA. Nation Survey of Child Health
| Percentage of CYSHCN aged 6-17 who have medical, behavioral or other health conditions which interfere with their ability to attend school regularly, participate in sports or other activities, or make friends? | 30.3 | 2007 | HRSA. Nation Survey of Child Health
PRIORITY #2: CYSHCN receive services necessary to make transitions to all aspects of adult life, including adult health care, work and independence.
Transitioning | Indicator | KS Measure | Year | Data Source
| Percentage CYSHCN (12-17 years) who receive the services necessary to make appropriate transitions to adult health care, work and independence | 41.2 | 2005/2006 | HRSA. Nation Survey of CSHCN
| Percentage of recipients successfully transition from Part C to Part B | 100 | 2009 | Infant toddler program data.
| Percentage YSHCN receive all anticipatory guidance for transition to adult health care | 32.4 | 2005/2006 | HRSA. Nation Survey of CSHCN
| Percentage YSHCN whose doctors usually or always encourage development of age appropriate self management skills | 78 | 2005/2006 | HRSA. Nation Survey of CSHCN
| Percentage of CYSHCN program (15 and older) participants who found an adult doctor | 25 | 2009 | CYSHCN special survey
| Percentage of CYSHCN program (15 and older) participants who found an adult specialist | 26 | 2009 | CYSHCN special survey
| Percentage of CYSHCN program (15 and older) participants who know when to report changes in their health | 54 | 2009 | CYSHCN special survey
| Percentage of CYSHCN program (15 and older) participants who know how to get emergency help | 66 | 2009 | CYSHCN special survey
| Percentage of CYSHCN program (15 and older) participants who can take responsibility for their health needs at home | 51 | 2009 | CYSHCN special survey
| Percentage of CYSHCN program (15 and older) participants who can take responsibility for their health needs at school or work | 51 | 2009 | CYSHCN special survey
| Percentage of CYSHCN program (15 and older) participants who can follow medical directons | 54 | 2009 | CYSHCN special survey
| Percentage of CYSHCN program (15 and older) participants who have plans where to live as an adult | 42 | 2009 | CYSHCN special survey
| Percentage of CYSHCN program (15 and older) participants who can arrange transportation | 39 | 2009 | CYSHCN special survey
| Percentage of CYSHCN program (15 and older) participants who have information about school or tech training | 28 | 2009 | CYSHCN special survey
| Percentage of CYSHCN program (15 and older) participants who have skills to live independently | 36 | 2009 | CYSHCN special survey
| Percentage of CYSHCN physician who always or usually report that the treatment plan addresses youth development in assuming personal care/management and transition planning to adult medical providers? | 35.9 | 2009 | CYSHCN special survey
PRIORITY #3: Financing for CYSHCN services minimizes financial hardship for their families.
Impact on Families | Indicator | KS Measure | Year | Data Source
| % CYSHCN whose families pay $1,000 or more out-of-pocket | 21.9 | 2005/2006 | HRSA. Nation Survey of CSHCN
| % CYSHCN whose conditions cause financial problems for family | 21.4 | 2005/2006 | HRSA. Nation Survey of CSHCN
| % CYSHCN whose families spend 11 or more hours a week providing health care | 8 | 2005/2006 | HRSA. Nation Survey of CSHCN
| % CYSHCN whose conditions cause family members cut back or stopped working | 20.1 | 2005/2006 | HRSA. Nation Survey of CSHCN
| % CSHCN (0-5 years) Parents who report at least one child care or employment issues | 47.4 | 2007 | HRSA. Nation Survey of Child Health
| % CSHCN (0-5 years) Parents who report childcare effects employment | 14 | 2007 | HRSA. Nation Survey of Child Health
| % CSHCN (0-5 years) Parents who made different arrangements for child care at the last minute due to circumstances beyond your control and had no problems | 44 | 2007 | HRSA. Nation Survey of Child Health
| % CSHCN (6-11 years) who spends some time alone | 18.2 | 2007 | HRSA. Nation Survey of Child Health
| % CYSHCN who have inadequate insurance | 24.7 | 2007 | HRSA. Nation Survey of Child Health
| % CYSHCN have inadequate insurance | 30.1 | 2005/2006 | HRSA. Nation Survey of CSHCN
| % CYSHCN parents whose out-of-pocket expenses are never or sometimes reasonable | 18.9 | 2007 | HRSA. Nation Survey of Child Health

## Essential Services List
10 Essential MCH Services
<None Selected>
1. Assess/monitor health status of women and children to ID/address problems
2. Diagnose/investigate problems and hazards affecting women, children, youth
3. Inform/educate the public/families about MCH issues
4. Mobilize community partnerships to solve MCH issues
5. Leadership in setting priorities, planning and policy development
6. Promote legal requirements to protect the health and safety of MCH population
7. Link women & children with services and assure quality systems of care
8. Assure work force capacity and competency
9. Evaluate effectiveness, accessibility, quality
10. Support research and demonstration projects